## WG1
WG1 Milestones | Bulk Nb SRF Milestones | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding |  | Collaborators |  | Comments
[7 empty] | FTE's | Capital Cost | Existing | New | Existing | New
@ 5 years | Push forward the development and validation of large/medium grain material
| Operational CW cryomodule at gradients > 20 MV/m | [7 empty] | LCLS-II | N/A | FNAL/Jlab/SLAC | N/A | 20.8 MV/m being achieved for LCLS-II HE (it is only achieved with Fine Grain; milestone needs to be pushed forward for MG et LG)
| Develop new vendors of LG/MG ingots to allow mass production | [11 empty] | This will be done when a project will have a need (timeschedule is linked to project)
Scale to lower frequencies than 1.3 GHz (larger cavities).
@ 5 years | Continue R&D on vacuum heat treatment
| Push further investigation of the annealing (mid-T, 2 steps , etc) | [7 empty] | PIP-II ILC ITN |  | INFN-LASA/STFC INFN-LASA INFN-LASA/CERN/CEA/DESY/KEK |  | Demonstrable capability established, being used actively for PIP-II LB650 cavities. Working on R&D for H Q, H gradient
| Demonstrate improvements and applicability of these advanced heat treatment for other frequencies than 1.3 GHz. | [11 empty] | See above, being applied for PIP-II at 650 MHz
Apply advanced heat treatments as standard treatment for new accelerator projects
@ 5 years | Improvement of surface treatment : surface polishing and characterisation techniques: standard techniques (EP, BCP), developing new techniques (EPP, MP, etc.), and doping
| Develop new infrastructures for large cavities (multicells, low beta, etc.): cold EP, rotational BCP | [7 empty] | PIP-II ILC ITN |  | INFN-LASA/STFC, IJCLab INFN-LASA INFN-LASA/CERN/CEA/DESY/KEK |  | This has been done in the industry for PIP-II CERN, STFC, CEA, INFN-LASA are all building capability
Investigate and develop doping and infusion
Investigate, identify and optimize polishing techniques compatible with SRF requirements and industrialisation
New and advanced polishing techniques mature for new accelerator projects
@ 5 years | Develop robotisation/cobotisation (human-robot collaboration) for surface processing/cleaning of SRF components
| Operational robot in clean rooms and demonstrate improved cleaniness | [11 empty] | CEA has a cobot in the clean room, Cleaning of ESS components routinely, IJCLab candidate Development towards assembly of components on FNAL, CEA, IMP, KEK
Apply as standard for new accelerator projects
@ 5 years | Pursue R&D effort on X-rays diagnostics capabilities.
| Show improved efficiency and yield of surface preparation | [11 empty] | DESY, CEA, IJCLab, ESS, Univ Ham, INFN-LASA, CERN
Apply as standard diagnostics for new accelerator projects
@ 5 years | Intensify R&D on field emission mitigation/in-situ recovery techniques (dry-ice, plasma).
| Deployment and show efficiency of these techniques for accelerator in operation. | [11 empty] | Development towards assembly of components: IJCLab, DESY
apply as standard pre-treatment or recovery treatment for new accelerator projects

## WG2
WG2 | Thin Film SRF (Yellow Report CERN-2022-001 Milesones - MS) | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding |  | Collaborators |  | Comments
[7 empty] | FTE's | Capital Cost | Existing | New | Existing | New
@ 5 years | Continue R&D niobium on copper—construction cost saving and securing supply:
| Reach bulk niobium performances on 1.3–0.4 GHz elliptical and various cavity shapes (WOW, SWELL). |  |  | 1st prototype |  |  | 28 | 6M€ | 0.8M€ |  | INFN, CAE, STFC/CI, |  | By 2025, >4 cavities to be coated and tested, 50% expected to perform comparable to bulk Nb
| scale up process to multicellular cavities (1.3–0.6 GHz) | [9 empty] | USI, Hamburg U, STFC |  | R&D starts in 2025, 1st cavity coating expected after 2026
@ 5 years | Intensify R&D of new superconductors on Cu—4.2 K operational cost saving
| A15 (Nb3Sn, V3Si, etc.): reach same performance as Nb3Sn on Nb at 4.2 K on several cavity geometry (1.3–6 GHz). |  |  |  | 1st prototype | [5 empty] | INFN, CAE, STFC/CI, USI |  | By end of 2026, >4 cavities to be coated and tested, 50% expected to perform comparable to bulk Nb
| MgB2: feasibility (critical temperature > 30 K) on 1.3 GHz cavity. |  | only on samples | [7 empty] | STFC |  | not possible without additionnal funds
| Study the influence of mechanical deformations and induced strain (∼0.1 %) of cavities on the RF performances of A15 and MgB2 alloys. |  |  |  | only Nb3Sn | [5 empty] | INFN, HZB, STFC/CI |  | Work within ISAS - only Nb3Sn, no funduing for other materials
| MS-i. A15: reach same performances at 4.2 K as bulk Nb at 2 K, scale to other frequencies (elliptical) and investigate the potential for multicell cavities. |  |  |  | 1st prototype | [7 empty] | Hard or impossible to progress without additional funding
| MS-ii. MgB2: reach same performances at 4.2 K as bulk Nb at 2 K. | [11 empty] | Impossible to progress without additional funding
@ 5 years | Pursue multilayers—push for high gradient
| Demonstrate increased acceleration on 1.3 GHz bulk Nb and thin-film Nb/Cu 1.3 GHz elliptical cavity |  |  | 1st prototype |  |  | 11 | 6M€ | 0.2M€ |  | INFN, STFC/CI |  | Multiple tests on cavities required
| scale up to various cavity shapes and multicell elliptical cavities | [11 empty] | Impossible to progress without additional funding
@ 5 years | Intensify Cu cavity production and surface preparation
| Seamless elliptical Cu substrates (mechanical or electro-deposited) starting at 1300 MHz down to 400 MHz |  | 1st prototype (INFN) | [6 empty] | ?? | INFN, CERN | ?? | SRF community already tightly knit. Some informal collaborations could become formal. New collaboration could arise from new comers, e.g. in material science. Could be triggered easily if some "subcontracting money" has been foreseen.
| Optimise air stable chemistries (EP-BCP/without liquid waste, heat treatment, passivation layers, etc.) for Cu surface preparation |  | 1st test | [7 empty] | INFN, CERN, IJClab, RTU, HZDR, CEA |  | Work is mostly on samples. Hard or impossible to progress without additional funding
| scale up processes to multicell cavities (1.3 GHz) | [11 empty] | Impossible to progress without additional funding
@ 5 years | Develop 3D printing and innovative cooling techniques.
| Develop proper substrate Cu/Al alloys (monocellular cavity 3.9 and 1.3 GHz) for thin film deposition with optimised density (> 99.8%), cooling power and mechanical response (similar to Nb at 4.2 K). | [9 empty] | CEA, CERN, INFN, RTU |  | Issues: high initial cost of 3D machine (millions euro) and consumables, maximum product size is limited. No funding at CEA to continue work
| Demonstrate substrate (cavities) surface roughness |  | 1st test | [7 empty] | CEA, CERN, INFN, RTU |  | Mostly on samples
| Demonstrate conduction cooled cavities with selected and optimised innovative heat links and a cryocooler | [9 empty] | CEA, CERN, RTU
| MS-i. Demonstrate bulk Nb performances with thin Nb film on 3D printed/electro-deposited cavity at 4.2 K. | [11 empty] | Not possible untill Task 1 is achieved; after 2025
| MS-ii. Demonstrate bulk Nb performances with new superconductors (A15, MgB2) film on 3D printed/electro-deposited cavity at 4.2 K. | [11 empty] | Not possible untill Task 2 is achieved; after 2026
| MS-iii. Develop proper substrate multicell cavities. | [11 empty] | Not possible untill Tasks 1 & 2 is achieved; after 2027
@ 5 years | Infrastructures and manpower—high-throughput testing
| Dedicated building with thin-film specific state-of-the-art infrastructures (clean rooms, chemistry, rinsing/washing, assembly). |  |  |  |  | 2028 @ CERN |  |  |  |  | CERN
| Improved surface characterisation methods (spectroscopy, QPR) and cold test diagnostics (temperature mapping on Cu, automated optical inspection, etc.). |  |  |  | ongoing | [5 empty] | INFN, CERN, IJClab, HZDR, CEA, STFC |  | Ongoing process: need for continues investement for in-lab equipment and for paying the cost at external labs
| Reinforced International Student and collaboration effort program. | [11 empty] | Impossible without dedicated funding
| High-throughput RF testing facility to establish repeatable and reliable performance needed in preparation of series production. | [11 empty] | Need for manpower and budget for LHe to produce the results

## WG3
WG3 Milestones | Couplers (FPC and HOM) | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding |  | Collaborators |  | Comments
[7 empty] | FTE's | Cost | Existing | New | Existing | New
@ 5 years | Build or upgrade a fully equipped bench for room-temperature high-power RF testing of 1 MW class CW FPCs | [5 empty] | 1 | 1500k |  | FCC |  |  | Zero progress
| Demonstrate the feasibility of room temperature windows with equivalent power handling as the current state of the art, based on both high-purity and low SEY ceramic. | [5 empty] | 0.3 | funded | CERN |  |  |  | Zero progress, lack of manpower
| Fast reactive tuners: demonstrate transient detuning at 400 MHz. | [6 empty] | funded | CERN |  | Lancaster |  | A transient detuning demonstrator was designed and built and is waiting for a test.
| FRT 1.3 GHz microphonics compensation: Testing of Ferroelectrica | [7 empty] | HZB |  | CERN |  | FRT 1.3 GHz microphonics compensation: Testing of Ferroelectrica, FE-FRT cavity prototype manufacturing and testing (2024-27), FTEs 1, fundet via iSAS; In 2023 a characterisation teststand for 1.3 GHz was has been already ordered
| Conceptual studies of novel FPC architectures and selection of the more promising ones for further prototyping. | [6 empty] | funded | FCC |  |  |  | Progress on the electrical and mechanical design.
| Demonstrate the performance at room temperature of a 400 MHz power coupler at 1 MW CW. | [5 empty] | 2 | 700k |  | FCC | - |  | Zero progress on hardware so far due to lack of funding. Needs to demonstated by 2029.
@ 10 years | Demonstrate the performance in cryomodule-like conditions of a power coupler at 1 MW CW. - Aspirational
Start industrialisation for series production. - Aspirational

## WG4
WG4 Milestones | NV Very High Gradient | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding |  | Collaborators |  | Comments
[7 empty] | FTE's | Cost | Existing | New | Existing | New
@ 5 years | General NC RF studies covering new geometries, breakdown studies, dark current modelling and simulations
| RF design of an accelerating structure for the klystron based CLIC RF module with the new type of cells with integrated HOM damping loads, ’rectangular disks’. RF design of RF pulse compression system with correction cavities for the klystron based CLIC RF module. RF design study of accelerating structures for CLIC main linac with distributed coupling. | [5 empty] | 3 | 150kEuro | CERN |  | CERN
| Optimisation of electromagnetic constructive design of X-band high-gradient structures to be operated with klystrons and pulse compression for EuPRAXIA project, synergic with similar linac projects. Modelling dark current production and transport, and benchmark it against experimental data | [5 empty] | 3 | 150kEuro | INFN Frascati |  | INFN Frascati
Development of high-gradient, high-duty cycle RF cavities - Aspirational
RF Breakdown studies using flat samples. - Aspirational
@ 5 years | NC RF manufacturing technology
| Supervision and qualification of copper-cells manufacturing companies, assembling and brazing in-house complete structures. Study and test of alternative, brazing-free construction process | [5 empty] | 2 | 1MEuro | CERN, INFN Frascati |  | CERN, INFN Frascati
| Design and fabrication of prototypes of the new type of cells with integrated HOM damping loads, rectangular disks’. Fabrication of an accelerating structure prototype for the klystron based CLIC RF module. Design and fabrication of RF pulse compression system with correction cavities for the klystron based CLIC RF module. | [5 empty] | 2 | 1MEuro | CERN |  | CERN
| Development of ’rectangular disks’ and work with companies to manufacture X-band cavities including RF testing. | [5 empty] | 2 | 1MEuro | CERN |  | CERN
@ 5 years | MM-wave and higher frequency structures
| Development of beam dynamics for scalable mm-wave linacs | [7 empty] | University of Lancaster
| Demonstration of scalable staging of mm-wave acceleration (including beam dynamics) | [7 empty] | University of Lancaster
Demonstration of Ka-band high-gradient acceleration - Aspirational

## WG5
WG5 Milestones | High-efficiency klystrons & solid-state amplifiers | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding |  | Collaborators |  | Comments
[7 empty] | FTE's | Cost | Existing | New | Existing | New
@ 5 years | Simulations & design of high-efficiency klystrons | [7 empty] | CERN | STFC | ULAN |  | Covered by CERN HE klystron program. FCC TS Klystron design complete including collector design, and ability to change power while conserving effciiency by varying DC voltage. Foxus now on X-band tubes.
| Prototype of LHC plug-compatible high-efficiency klystron | [7 empty] | CERN |  | Thales |  | FAT test scheduled to Spring 2023
| Design of power combining cavities | [11 empty] | No advancement or commitments
| Conceptual designs for high-efficiency klystrons | [7 empty] | CERN | STFC | ULAN |  | Two-stage klystron concept has been developed and is moving to prototyping, now looking into smart modulators to allow operation at satuation. Activities with permanent magnets are progressing.
| 1 FCC CSM or 2 stage L-band klystron prototype (400–800 MHz); | [7 empty] | CERN | STFC | ULAN, Thales(?) |  | Design study will be completed by 2023. Prototyping and tests with industry 2024-26
| X-band 50 MW high-efficiency klystron prototype | [7 empty] | INFN |  | CPI,CERN |  | FAT test scheduled to December 2024
| X-band 1.6 kW prototype solid-state klystron driver amplifier; | [11 empty] | No advancement or commitments
| Low-power prototypes of solid-state power combining systems | [11 empty] | No advancement or commitments
| RF power system concept for muon collider. | [5 empty] | 4 | £20k | EU |  | ULAN, CERN |  | Delayed 1 year due to Brexit related issues
| CERN high-efficiency klystron replacements for LHC before end-of-lifetime of existing devices to increase power into cavities (16 klystrons in total). - Aspirational | [7 empty] | CERN |  | Thales |  | The aspirational option is now considered as a baseline for HL-LHC. 16 klystron will be replaced at a speed of four per year, starting from 2025.
More likely: ∼6 new klystrons + gradual replacement towards end-of-lifetime. - Aspirational
| High-power prototypes of various solid-state power combining systems. - Aspirational | [11 empty] | Nov 2023: ESS is currently in the process of setting up a contract for a collaboration between ESS and Uppsala University for the development, construction and test of a 400 kW SSPA. This is a 2.5 year development.
Develop RF power sources concept for muon cooling complex RF system. Set target specifications and address potential issues (frequencies, peak power, efficiency). - Aspirational
@ 5 years | MM-wave & gyro-devices | [5 empty] | 2 | 0 |  | STFC, D, EU | KIT, Strath |  | Work set back by passing of A Cross
| Scoping study of short pulse mm-wave gyro-devices for linacs | [5 empty] | 5 | £20k |  | STFC, D, EU | KIT, Strath |  | Work set back by passing of A Cross
| Perform an electromagnetic design of mm-wave gyro-devices | [5 empty] | 9 | £1M |  | STFC, D, EU | KIT, Strath |  | Work set back by passing of A Cross at Strathclyde but work is progressing on Ka-band gyrodevices for RF undulators.
| Development of Gyrotron prototypes at 36 and 300 GHz and development of a 36 GHz klystron prototype - Aspirational | [11 empty] | 36 GHz upconverter design work at INFN is progressing, other 36 GHz work paused due to lack of funding post compactlight.
@ 5 years | Technologies to reduce RF power needs for acceleration
Performing conceptual studies adapted specifically to LHC, FCC, muon colliders and ERLs
| Design and build prototypes for the LHC transient detuning | [11 empty] | Fast reactive tuners for transient detuning were moved to WG3
Design and build prototypes for ERL operation (e.g. FCC-eh, PERLE) - Aspirational
Design and build prototypes for FCC-ee transient detuning. - Aspirational

## WG6
WG6 Milestones | Low-level RF, Machine Learning, Artificial Intelligence | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding |  | Collaborators |  | Comments
[7 empty] | FTE's | Cost | Existing | New | Existing | New
@ 5 years | Development and implementation of µTCA based LLRF & control system for the HL-LHC superconducting crab cavities. Improved methodology + infrastructure. Continued development of white rabbit framework and components
Development of µTCA based LLRF & control system for the LHC elliptical superconducting accelerating cavities
@ 10 years | Implementation of centralised computing infrastructure for FPGA design. - Aspirational
Development and installation of standardised System-On-Chip LLRF prototypes for new machines and as replacement of legacy Versa Module Eurocard (VME) systems. Increased use of machine learning algorithms for operation. - Aspirational
Use RF test stands as development beds for new LLRF modules (e.g. µTCA, system on chip, etc.). - Aspirational
LLRF networking events and increased coordination effort between European laboratories. - Aspirational
@ 5 years | Artificial intelligence and machine learning - plan consists of several work program developed at CERN, STFC and DESY. For CERN, the effort is embedded in operation and commissioning
For STFC, the plan is to perform further studies 83 3. High-gradient RF structures and systems on X-box & CLARA data and start SRF studies (develop predictive AI to detect breakdown and other trips)
For DESY, the program is to perform SRF studies to provide a complementary AI algorithm to detect SRF cavity quenches along with other anomalies observed within the LLRF systems
To classify anomalies and implement a demonstrator for live data analysis (i.e. running with live data)
Test on-line running and control via AI on test stand: decrease conditioning time on test stands using AI;
Running detection live on the entire EuXFEL;
Automatic categorisation / labelling of trips for SRF cavities.
@ 10 years | Demonstration of an operating machine of AI control: decrease machine trips of an operating machine using AI - Aspirational
For SRF, extending the AI monitoring to other subsystems (klystrons, cryogenics) - Aspirational
For SRF, extending the functionalities of the online AI to self-calibration of LLRF systems, predictive diagnostics and automatic preventive countermeasures - Aspirational

## Infrastructures
| Test Infrastructure | 2022 | 2023 | 2024 | 2025 | 2026 | Needed |  | Funding Route |  | Collaborators |  | Comments
[7 empty] | FTE's | Capital Cost | Existing | New | Existing | New
NC RF | CERN: X-box #1 #2 #3;INFN Frascati: TEX; PSI: C-band test stand for structures/modules; Valencia: S-band test stand for structure; Cockcroft Institute: S-band test stand under construction.
(WG4, WG3, ...) | • Operation, maintenance and upgrade of CERN Xboxes #1, #2 and #3
• Construction of High gradient test stand at Daresbury. Study of RF breakdown on flat samples. Testing of new structure types.
• Valencia and INFN-TEX: test of 5 X-band devices/year for the next 5 years,
• Increased capacity of the Daresbury test stand.
• INFN TEX: adding capability to operate power tests also in S/C bands for expanded high gradient activities. High cathode peak field tests of RF guns (200 MV/m goal, C-band).
Test stands for new materials resilient to beam losses and RF breakdown in vacuum
(WG1, WG4, ...) | • Cryogenic DC test of copper electrodes down to 30 K.
• Testing different irradiated materials.
• Study of conditioning.
• DC testing of electrodes from different material including: OFE Cu, CuCrZr, TiAl6V4, Nb, Ta, CuBe before and after irradiation. Fabrication, preparation and evaluation of electrodes.
• Upgrade cryogenic DC test system to reach temperatures below 10 K.
• DC test of superconducting electrodes (niobium).
• Equipped DC test system with portable clean room for electrode installation.
RF design and implementation of low/medium energy high-gradient linacs
(F. Gerigk, D. Alesini) | • operation of CERN facilities (AWAKE, CLEAR); | [6 empty] | funded | CERN |  |  |  | Prolongation beyond is planned but still needs to be formally approved in 2024.
• realisation of a full RF module prototype for the EuPRAXIA@SPARC_Lab project (INFN);
• realisation and test of a high-gradient, high-repetition rate C-band RF gun (INFN).
RF test stand and test cavities for R&D on high-gradient NC RF in strong magnetic fields
(WG4, G. Burt, link to MC-Panel) | • design and build a RF test stand based on the available infrastructure and specific requirements; | [5 empty] | 24 | 10M | Cockcroft | EU, National funding | CERN, INFN, CEA, Cockcroft, ISIS, Southampton |  | Cockcroft bunker is funded without magnet
| • develop a test program adapted to the test stand, considering possible limitations in terms of available frequency, power, magnetic field strength and size of a SC solenoid; | [5 empty] | 1 | 0 | MuCol |  | CERN, INFN, CEA, Cockcroft, ISIS, Southampton |  | Planning is ongoing but depends on funding
| • design, build and test the prototype cavities. | [5 empty] | 8 | 1M |  | EU, National funding | CERN, INFN, CEA, Cockcroft, ISIS, Southampton
Technical infrastructure for fully dressed superconducting cavity testing up to cryomodule testing
(all) | • Develop an R&D program on bare cavities (even sometimes on simplified geometry such as monocell cavities, or reduced size cavities for cost efficiency reasons) • Develop cold RF test stand for performance | [11 empty] | This is done in all labs concerned by a new project
| • Vertical test stand for cavities at high rate | [11 empty] | Existing at DESY, JLab, FNAL
• Develop an R&D program for the associated ancillaries systems (power couplers, tuners, HOM) specifically adapted to the need and geometries of the cavity. This part integrates separated tests of each sub-system for their individual validation.
| • Assess the overall performance of the fully dressed cavity (cavity equipped with its ancillaries) at the nominal operation temperature and RF power in horizontal test bench | [11 empty] | DESY, CEA, ICLAb, Upsaala, CERN
• Perform the engineering design of the complete cryomodule integrating the outcomes of the preceding program and build a prototype cryomodule.
| • High power test of the prototype cryomodule for the full assessment of its performances. | [11 empty] | CEA, IJCLab, DESY, CERN, Upsaala
| • High power test of the cryomodule for the full assessment of its performances at high rate | [11 empty] | Existing at DESY, JLab, FNAL, ESS